## Full Backlog
LinkedBloom Scribe — Product Backlog
Story ID | Sprint | Epic | Feature | User Story | Acceptance Criteria | Dependencies | Priority | Status | Notes
US-001 | S1 | Epic 1: Foundation | 1.1 DB Migration | As a developer I want to run a DB migration adding all missing columns to the posts table so that no application data is silently lost | • Migration file at supabase/migrations/[ts]_add_posts_columns.sql • Adds: hashtags text[], topic, tone, instructions, post_length, versions jsonb, scheduled_at, published_at, linkedin_post_id, source_inspiration_url, performance_data • Runs without error on existing data • Existing rows unaffected (NULL in new columns) • Idempotent | None | P0 | To Do
US-002 | S1 | Epic 1: Foundation | 1.1 DB Migration | As a user I want my post's topic, tone, instructions, hashtags, and length saved when I generate content so that I can regenerate with the same settings | • contentService.createPost() writes all new fields • contentService.updatePost() updates all fields • contentService.getPost() returns all fields • Post TS type updated — no type errors • Existing posts load without error | US-001 | P0 | To Do
US-003 | S1 | Epic 1: Foundation | 1.4 Version History | As a user I want every version of my post saved automatically so that I can go back to a previous draft after page refresh | • generate-content Edge Function appends new version to versions JSONB array • Version shape: {version_number, content, title, hashtags, generated_at, model_used, instructions_used} • Version number auto-increments • Regenerate also creates new version • ContentPreview shows version list with timestamps • Restore button replaces editor content (non-destructive) • Version count badge on post cards | US-001,US-002 | P0 | To Do
US-004 | S1 | Epic 1: Foundation | 1.2 Calendar | As a user I want to see my actual scheduled and published posts on the calendar so that I can understand my real posting schedule at a glance | • Calendar fetches posts WHERE status IN ('scheduled','published') from Supabase • Posts on correct date: scheduled_at or published_at • Loading skeleton during fetch • Empty state when no posts • Real-time update in same session • All mock initialScheduledContent removed | US-001 | P0 | To Do
US-005 | S1 | Epic 1: Foundation | 1.2 Calendar | As a user I want to pick a date/time to schedule my post so that it appears on the calendar and publishes automatically | • 'Schedule Post' button on final-status post opens date-time picker • Shows user local timezone • Cannot select past date • On confirm: status='scheduled', scheduled_at set in DB • Success toast shown • Post appears on calendar immediately • Post card shows 'Scheduled' badge with date | US-001,US-004 | P0 | To Do
US-006 | S1 | Epic 1: Foundation | 1.2 Calendar | As a user I want to change the scheduled date of a post from the calendar so that I can adjust my plan without going to the editor | • Click scheduled post → post detail panel • Panel shows: title, preview, current date, Reschedule / Unschedule / Edit buttons • Reschedule opens date-time picker pre-filled • On confirm: scheduled_at updated in DB, calendar reflects immediately • Edit navigates to editor • Success toast on reschedule | US-004,US-005 | P0 | To Do
US-007 | S1 | Epic 1: Foundation | 1.2 Calendar | As a user I want to remove a post from my schedule directly from the calendar so that I can quickly unschedule without navigating to the editor | • 'Remove from schedule' button in panel (not delete — just unschedule) • Confirmation dialog • On confirm: scheduled_at=NULL, status='draft', disappears from calendar • Post still in drafts list as 'draft' • Separate 'Delete permanently' with two-step confirm • Permanently deleted post removed from DB | US-004,US-005 | P0 | To Do
US-008 | S1 | Epic 1: Foundation | 1.3 Settings | As a user I want to click Settings in the sidebar and land on a real page so that I don't hit a 404 | • /settings route defined in React Router • Page renders with sidebar layout and active nav highlight • Four sections visible: Profile, API Keys, Notifications, Danger Zone • No console errors on load | None | P0 | To Do
US-009 | S1 | Epic 1: Foundation | 1.3 Settings | As a user I want to update my profile details in Settings so that my persona and content generation always uses accurate information | • Form pre-filled from profiles table • Editable: full_name, job_title, industry, experience_level, location, linkedin_url, goal • Save updates profiles table • Success toast on save • LinkedIn URL validated as linkedin.com/in/ format • Changes reflected in sidebar immediately | US-008 | P0 | To Do
US-010 | S1 | Epic 1: Foundation | 1.3 Settings | As a user I want to manage my Gemini and OpenAI API keys in Settings so that content generation uses my own quota | • Masked input fields for Gemini and OpenAI keys • Existing keys shown masked (last 4 chars visible) • 'Update key' clears mask for re-entry • Save stores key encrypted in Supabase • 'Remove key' clears from DB with confirmation • Keys validated with test API call on save • Edge Functions use user key (fall back to system key if not set) | US-008 | P0 | To Do
US-011 | S1 | Epic 1: Foundation | 1.3 Settings | As a user I want to configure which notifications I receive so that I'm reminded about my schedule without being overwhelmed | • Toggles: remind 1h before post (ON), weekly digest (ON), publish confirmation (ON), engagement milestones (OFF) • Persist to profiles.notification_preferences jsonb • Auto-save on toggle • Email sending wired in Sprint 6 | US-008 | P0 | To Do
US-012 | S1 | Epic 1: Foundation | 1.3 Settings | As a user I want to permanently delete all my data from Settings so that I can trust the platform respects my right to be forgotten | • Danger Zone section with red styling • 'Delete all my data' button opens modal • Modal: warning text + type 'DELETE' to confirm + red confirm button • On confirm: deletes all rows from posts, personas, chat_messages, post_analytics, engagements, inspirations, extension_events, linkedin_accounts • Deletes all user storage files • Calls auth.admin.deleteUser() • User redirected to landing page • Action irreversible — no soft delete | US-008 | P0 | To Do
US-013 | S2 | Epic 2: LinkedIn | 2.1 OAuth | As a developer I want a linkedin_accounts DB table so that user OAuth tokens can be stored securely | • Migration creates linkedin_accounts (id, user_id, linkedin_member_id, access_token_encrypted, refresh_token_encrypted, token_expires_at, scopes[], connected_at, last_refreshed_at, is_active) • RLS enabled • Unique index on (user_id) WHERE is_active=true | None | P1 | To Do
US-014 | S2 | Epic 2: LinkedIn | 2.1 OAuth | As a user I want to connect my LinkedIn account via OAuth so that the platform can publish posts on my behalf | • 'Connect LinkedIn' in Settings initiates OAuth 2.0 PKCE flow • Edge Function generates code_verifier + code_challenge • Redirect to LinkedIn with correct scopes: w_member_social, r_liteprofile, r_emailaddress, r_organization_social • /auth/linkedin/callback route in React Router • Callback Edge Function exchanges code for tokens using code_verifier • Tokens AES-256 encrypted before storage • linkedin_member_id stored from /v2/me call • User redirected to Settings with success message | US-013 | P1 | To Do
US-015 | S2 | Epic 2: LinkedIn | 2.1 OAuth | As a user I want to see my LinkedIn connection status across the app so that I always know the connection state | • Settings shows 'Connected as [name]' with green badge if token active • 'Disconnect' button shown when connected • Dashboard header shows connection status indicator • If token expired: 'Reconnect required' with orange badge • 'Publish to LinkedIn' button disabled with tooltip if not connected | US-014 | P1 | To Do
US-016 | S2 | Epic 2: LinkedIn | 2.1 OAuth | As a user I want to disconnect my LinkedIn account so that I can revoke access at any time | • 'Disconnect' button in Settings → LinkedIn • Confirmation modal with warning about scheduled posts • On confirm: is_active=false, tokens cleared • Status updates to disconnected immediately • Publish button disabled across app | US-015 | P1 | To Do
US-017 | S2 | Epic 2: LinkedIn | 2.1 OAuth | As a developer I want automatic token refresh so that users never have to manually reconnect due to token expiry | • Edge Function: linkedin-refresh-token • Fetches users where token_expires_at < now() + 1 hour • Calls LinkedIn token refresh endpoint • On success: updates access_token_encrypted, token_expires_at, last_refreshed_at • On failure: is_active=false, notification queued • pg_cron job every 30 minutes • Operations logged without token values | US-014 | P1 | To Do
US-018 | S2 | Epic 2: LinkedIn | 2.2 Publishing | As a developer I want a linkedin-publish-post Edge Function so that the client never handles LinkedIn tokens | • Accepts: post_id (uuid) • Fetches post content + hashtags from posts table • Decrypts user's access token • Constructs LinkedIn UGC Post payload • POSTs to /v2/ugcPosts • On success: status='published', linkedin_post_id, published_at set in DB • On failure: structured error returned • Token never logged or returned | US-014,US-013 | P1 | To Do
US-019 | S2 | Epic 2: LinkedIn | 2.2 Publishing | As a user I want to publish my post to LinkedIn with one click from the review page so that I can go from approved draft to live post | • 'Publish to LinkedIn' button on posts with status 'final' • Button disabled with tooltip if not connected • Confirmation modal with post preview • Loading state during API call • On success: status='published', success toast + 'View on LinkedIn' link • On failure: error toast, status unchanged • Published post shows LinkedIn badge + link + timestamp • Published posts read-only | US-018,US-015 | P1 | To Do
US-020 | S2 | Epic 2: LinkedIn | 2.2 Publishing | As a user I want scheduled posts to publish automatically at the scheduled time so that I don't have to be online at that moment | • pg_cron runs every 5 minutes • Queries posts WHERE status='scheduled' AND scheduled_at <= now() AND user has active LinkedIn connection • Calls linkedin-publish-post for each • On success: status='published', published_at set • On failure: status='publish_failed', error stored, user notified • Never processes same post twice | US-018,US-017 | P1 | To Do
US-021 | S2 | Epic 2: LinkedIn | 2.2 Publishing | As a user I want to see a direct link to my published post on LinkedIn so that I can check how it appears and share it | • Published posts show 'Published on LinkedIn' green badge • 'View on LinkedIn' button opens linkedin.com/feed/update/{id} in new tab • Published timestamp shown as relative time • Post content display is read-only • Published posts in 'Published' filter tab in drafts list • Post card shows: title, published date, quick engagement stats | US-019 | P1 | To Do
US-022 | S2 | Epic 2: LinkedIn | 2.3 Analytics | As a developer I want a post_analytics DB table so that LinkedIn metrics can be stored and queried without calling LinkedIn API on every page load | • Migration creates post_analytics (id, post_id, user_id, impressions, reactions, comments, shares, clicks, engagement_rate, fetched_at, fetch_period) • RLS enabled • Composite unique index on (post_id, fetch_period) | US-001 | P1 | To Do
US-023 | S2 | Epic 2: LinkedIn | 2.3 Analytics | As a developer I want a linkedin-fetch-analytics Edge Function so that post metrics are fetched and stored server-side | • Accepts: post_id, fetch_period • Fetches linkedin_post_id from posts • Calls LinkedIn /v2/organizationalEntityShareStatistics • Parses: impressions, reactions, comments, shares, clicks • Calculates engagement_rate • Upserts to post_analytics • Exponential backoff on 429 • Returns structured response | US-022,US-014 | P1 | To Do
US-024 | S2 | Epic 2: LinkedIn | 2.3 Analytics | As a user I want my post analytics automatically refreshed at 24h, 48h, 7d, 14d, and 30d so that I see how posts perform over time | • On post publish: schedule 5 analytics fetch jobs at +24h, +48h, +7d, +14d, +30d • Each job calls linkedin-fetch-analytics with correct fetch_period label • Jobs only run if LinkedIn connected • Failed fetches retried up to 3× with backoff • Fetch jobs for deleted posts cleaned up | US-023,US-019 | P1 | To Do
US-025 | S2 | Epic 2: LinkedIn | 2.3 Analytics | As a user I want a manual 'Refresh metrics' button on published posts so that I can get the latest data without waiting | • 'Refresh metrics' button on published post analytics view • Calls linkedin-fetch-analytics with fetch_period='manual' • Loading/disabled state during fetch • Success: metrics updated, last fetched timestamp shown • Rate limited: button disabled 15 min after last manual refresh • Error state if API fails | US-023 | P1 | To Do
US-026 | S3 | Epic 3: Analytics | 3.1 Dashboard | As a user I want real LinkedIn performance KPIs on my dashboard so that I can understand my actual reach and engagement at a glance | • KPI 1: Total Impressions (30d) • KPI 2: Total Reactions (30d) • KPI 3: Avg Engagement Rate (30d) • KPI 4: Posts Published (30d) • Trend indicators vs previous 30d • All mock KPI data removed • Data from post_analytics table • 'Connect LinkedIn' CTA if not connected | US-022,US-023 | P1 | To Do
US-027 | S3 | Epic 3: Analytics | 3.1 Dashboard | As a user I want to see my best performing post highlighted on the dashboard so that I understand what content resonates most | • 'Top Post This Month' card • Highest engagement rate post in last 30d • Shows: title (60 chars), published date, engagement rate, impressions, reactions • 'View post' and 'View on LinkedIn' links • Empty state if no published posts in 30d | US-026 | P1 | To Do
US-028 | S3 | Epic 3: Analytics | 3.2 Per-Post | As a user I want detailed analytics for each published post so that I can learn from each post's performance | • 'Analytics' tab on post detail (published only) • Shows: impressions, reactions, comments, shares, clicks, engagement rate • Engagement timeline: metrics at each fetch_period • Comparison to user average • 'What worked' AI insight (Gemini, cached on first view) • Export CSV button | US-022,US-023,US-026 | P1 | To Do
US-029 | S3 | Epic 3: Analytics | 3.3 Trends | As a user I want charts showing my engagement trends over time so that I can identify patterns and make informed content decisions | • /analytics route in sidebar • Impressions over time: line chart, 90 days • Reactions by topic: bar chart • Format breakdown: avg engagement by post_length • Tone breakdown: avg engagement by tone • Best day/time heatmap (requires ≥10 posts) • Progress state if <3 posts • All charts with recharts • Fully responsive | US-026,US-028 | P1 | To Do
US-030 | S3 | Epic 3: Analytics | 3.4 Import | As a user I want to import my existing LinkedIn posts so that I have a performance baseline and my analytics include pre-platform history | • 'Import LinkedIn posts' in Settings → LinkedIn • Edge Function: linkedin-import-posts fetches up to 50 recent posts • Stored with source='linkedin_import', status='published' • Deduplication by linkedin_post_id • Analytics fetched for each imported post • Progress indicator during import • Success message with counts • 'Imported' badge on imported posts • Included in all analytics calculations | US-014,US-023 | P1 | To Do
US-031 | S4 | Epic 4: Engagement | 4.1 Comment Drafting | As a developer I want an engagements DB table so that comment drafting sessions can be stored and reviewed | • Migration creates engagements (id, user_id, source_post_url, source_post_text, source_author, comment_options jsonb, selected_comment, posted_at, created_at) • RLS enabled • Indexes on user_id and created_at | US-001 | P2 | To Do
US-032 | S4 | Epic 4: Engagement | 4.1 Comment Drafting | As a developer I want a generate-comment-options Edge Function so that both web app and extension use the same comment generation logic | • Accepts: source_post_text, source_post_url (optional), user_id from JWT • Fetches active persona from personas table • Gemini generates exactly 3 options: agree-and-extend, clarifying question, respectful challenge • Each comment: max 200 words, in user's voice, no generic openers • Returns: [{approach, comment, character_count}] • All under 1,250 char LinkedIn limit • Response < 3 seconds | US-031 | P2 | To Do
US-033 | S4 | Epic 4: Engagement | 4.1 Comment Drafting | As a user I want to paste a LinkedIn post and get three on-brand comment options so that I can engage thoughtfully without spending time writing | • /engage route in sidebar • Tabbed input: paste text or paste URL • URL tab fetches post text (error if fails) • 'Generate comment options' button • Loading skeletons while generating • Three comment cards: approach label, text, character count bar • Copy / inline edit / Save engagement buttons per card • 'Regenerate all' and per-card regenerate • Saves to engagements table • History tab shows last 20 sessions | US-032 | P2 | To Do
US-034 | S4 | Epic 4: Engagement | 4.2 Inspiration Library | As a developer I want an inspirations DB table and storage bucket so that users can save and retrieve LinkedIn posts | • Migration creates inspirations (id, user_id, source_url, source_text, source_author, screenshot_url, note, tags text[], type, saved_at) • RLS enabled • Supabase storage bucket 'inspirations' private with user-scoped policies | None | P2 | To Do
US-035 | S4 | Epic 4: Engagement | 4.2 Inspiration Library | As a user I want to save LinkedIn posts that inspire me to a searchable library so that I can build a personal reference collection | • /inspiration route in sidebar • 'Add inspiration' opens slide-over panel • Fields: URL (optional), post text, author, note, topic tags • Screenshot drag-and-drop upload to Supabase storage • Inspiration card grid: thumbnail, URL link, note preview, tags, date • Search by keyword across text and note • Tag filter • Delete with confirmation • Empty state with guidance • Count badge on sidebar | US-034 | P2 | To Do
US-036 | S4 | Epic 4: Engagement | 4.2 Inspiration Library | As a user I want the content generator to consider my saved inspirations so that generated posts reflect the style and topics I admire | • Content generator fetches last 10 inspirations and includes as context in Gemini prompt • 'Use inspiration library' toggle (default ON) • When OFF: inspirations excluded from prompt • No visible UI change — content quality is the feature | US-034,US-035 | P2 | To Do
US-037 | S4 | Epic 4: Engagement | 4.3 Feed Insights | As a user I want AI-generated insights about patterns in my saved inspirations so that I understand what works in my niche | • 'Insights' tab on /inspiration page • 'Generate insights' button (manual trigger) • Requires ≥5 inspirations • Gemini analyses all saved inspirations and returns: top 3 topics, common hook patterns, dominant formats, avg post length, 'what makes it work' summary • Results as insight cards with examples • 'Create post using these patterns' → pre-fills content generator • Insights cached; 'Refresh insights' to regenerate • Last generated timestamp shown | US-035 | P2 | To Do
US-038 | S5 | Epic 5: Extension | 5.1 Scaffold | As a developer I want a properly structured Manifest V3 Chrome extension project so that all extension features can be built on a solid foundation | • /extension folder at repo root with own package.json • Vite + CRXJS plugin for Manifest V3 build • manifest.json with permissions: storage, activeTab, scripting + linkedin.com host_permissions • Background service worker registered • Content script for linkedin.com/* • Popup HTML + TS files • TypeScript configured • npm run dev builds to /extension/dist (loadable as unpacked) • npm run build for production • Icons: 16, 32, 48, 128px | None | P3 | To Do
US-039 | S5 | Epic 5: Extension | 5.1 Scaffold | As a user I want to be automatically logged into the extension when I'm logged into the web app so that I don't log in twice | • Web app writes Supabase JWT to chrome.storage.local as 'lb_session' on login • Web app clears 'lb_session' on logout • Extension popup reads 'lb_session' on open • Valid JWT: popup shows logged-in state with user name • No JWT / expired: shows 'Open LinkedBloom to log in' + link • Extension API calls include JWT in Authorization header • Session validity checked by JWT expiry — no extra API call | US-038 | P3 | To Do
US-040 | S5 | Epic 5: Extension | 5.1 Scaffold | As a user I want to open the extension popup and see my current status and quick actions so that I can control the extension without opening the full app | • Popup 320px wide, auto height • Logged-in state: logo, user name, monitoring status (green dot), pause/resume toggle, session stats, 'Open LinkedBloom' button, activity section • Paused state: grey dot, 'Monitoring paused', resume button • Logged-out state: logo, 'Log in to LinkedBloom' message, 'Open app' button • Footer: version, Privacy settings link, Help link | US-039 | P3 | To Do
US-041 | S5 | Epic 5: Extension | 5.1 Scaffold | As a user I want to see a clear explanation of what the extension monitors on first install so that I can make an informed decision about granting permissions | • On first install (detected via chrome.storage.local 'installed' flag): opens welcome page in new tab • Plain-English explanation: what is monitored, what stays local, what goes to cloud • Three permission toggles: feed monitoring (required), weekly topic sync (optional, default OFF), quick draft capture (optional, default ON) • 'Get started' saves preferences and closes tab • Preferences editable later from popup Privacy settings link | US-039 | P3 | To Do
US-042 | S5 | Epic 5: Extension | 5.2 Feed Detection | As a developer I want a MutationObserver that detects LinkedIn feed posts so that the extension can analyse posts as they load | • Content script initialises MutationObserver on linkedin.com/feed/* pages • Watches document.body with childList: true, subtree: true • For each new post node: extract author, post text (500 chars), post URL, reaction count, comment count • Handles standard posts and reposts • Processed posts stored in memory Map — no reprocessing • Observer paused when monitoring toggled off • No data sent to cloud | US-038 | P3 | To Do
US-043 | S5 | Epic 5: Extension | 5.2 Feed Detection | As a developer I want local post scoring so that only genuinely high-value posts surface to the user | • scorer.ts runs fully client-side • Score inputs: topic relevance (keyword match vs content pillars), comment count sweet spot (5–100), post recency (<6h high, 6-24h medium, >24h low), previously engaged author bonus • Score output: 0-100 integer • Badge threshold: ≥65 • Content pillars cached in chrome.storage.local from persona sync • Scoring < 50ms per post | US-042,US-039 | P3 | To Do
US-044 | S5 | Epic 5: Extension | 5.2 Feed Detection | As a user I want a subtle indicator on high-opportunity LinkedIn posts so that I don't miss valuable conversations in my feed | • Badge: small LinkedBloom icon (16px) top-right of post card for posts scoring ≥65 • Does not shift LinkedIn layout • Tooltip: 'Good engagement opportunity — click to draft a comment' • '×' dismisses badge for that post for session • Not injected on user's own posts • Not injected on already-commented posts • No new badges when monitoring paused | US-043 | P3 | To Do
US-045 | S5 | Epic 5: Extension | 5.3 Comment Overlay | As a user I want to click a badge and see AI-generated comment suggestions so that I can draft a thoughtful comment without leaving LinkedIn | • Clicking badge opens overlay panel anchored to post (340px wide) • Header: LinkedBloom logo, post author, '×' close • Loading skeleton while API call in progress • API call sends post text to generate-comment-options with JWT • Three comment cards with approach label and text • Character count (amber >800, red >1200) • 'Use this comment', 'Regenerate', 'Save to inspiration' buttons • Closes on outside click or Escape • State preserved while user scrolls | US-044,US-032,US-039 | P3 | To Do
US-046 | S5 | Epic 5: Extension | 5.3 Comment Overlay | As a user I want 'Use this comment' to insert text into LinkedIn's comment box so that I can review and post without copy-pasting | • 'Use this comment' injects text into LinkedIn native comment contenteditable div • Focus moves to comment box after injection • User can freely edit before posting • Extension does NOT click LinkedIn's Post button • Overlay closes after 'Use this comment' • If comment box not found: error with copy button fallback • Injected text triggers LinkedIn's native character count | US-045 | P3 | To Do
US-047 | S5 | Epic 5: Extension | 5.4 Quick Capture | As a user I want to capture a LinkedIn post as a draft inspiration with right-click on the badge so that I can build a queue of post ideas from my feed | • Right-click badge → context menu: 'Draft a comment', 'Capture as draft inspiration', 'Save to inspiration library', 'Dismiss' • 'Capture as draft inspiration' → generate-draft-from-capture Edge Function • Gemini generates new post inspired by (not copying) captured content, using persona • Draft saved to posts table: status='draft', source_inspiration_url • chrome.notifications: 'Draft created — review in LinkedBloom' • Works on standard posts, articles, reposts | US-044,US-039 | P3 | To Do
US-048 | S5 | Epic 5: Extension | 5.5 Transparency | As a user I want to see exactly what the extension has collected in this session so that I can trust it at any moment | • 'Activity' tab: posts scanned, badges shown, comments drafted, drafts captured — from chrome.storage.local • 'Privacy' tab: 'Stays on your device' list + 'Sent to cloud only when you act' list • 'Pause monitoring' toggle disconnects MutationObserver immediately • 'Clear session data' clears chrome.storage.local with confirmation • Link to full privacy page in web app • Counts update in real time (poll every 2s while popup open) | US-040,US-042 | P3 | To Do
US-049 | S6 | Epic 6: Persona | 6.1 Taste Intake | As a user I want to upload content samples and annotate what I like about them so that my persona reflects my actual aesthetic preferences | • 'Refine My Taste' section in Settings → Persona • Upload up to 10 samples: text, image, screenshot, URL • Per sample: annotation 'What do you like?' + tag selector • Visual style selector: 12 cards, pick up to 3 • All samples stored in inspirations table with type='taste_sample' • 'Update persona' button triggers persona refresh with taste context • Confirmation shown | US-034 | P4 | To Do
US-050 | S6 | Epic 6: Persona | 6.2 Persona Refresh | As a user I want to be prompted to refresh my persona every 30 days so that my voice profile stays accurate as I evolve | • In-app banner when now() > generated_at + 30 days • 'Refresh now' and 'Remind me in 7 days' options • Refresh opens PR agent chat in 'Persona Refresh' session • Gemini generates 3–5 contextual questions based on activity since last refresh • After answers: new persona generated with full context • Diff view: changed sections highlighted, unchanged greyed • User options: Accept all / Accept selected / Keep current • Previous persona archived (is_active=false, version++) • Manual trigger in Settings → Persona | US-009 | P4 | To Do
US-051 | S6 | Epic 6: Persona | 6.3 Behavioral Signals | As a user I want my LinkedIn engagement patterns to feed into my persona model so that the system learns from what I actually do | • Opt-in toggle in extension Privacy settings: 'Share weekly engagement patterns' (default OFF) • When opted in: weekly summary compiled — top 3 engaged topics, engagement style pattern, scan + draft counts • Synced to extension_events table (abstracted, not raw) • 'What we learned this week' card on dashboard • 'Mark as inaccurate' on any behavioural insight • Corrections stored in extension_events row • Behavioral summary included in next persona refresh context | US-042,US-050 | P4 | To Do
US-052 | S6 | Epic 7: Platform | 7.1 Notifications | As a user I want email reminders for scheduled posts and a weekly performance digest so that I never miss a scheduled post | • Resend API via send-notification-email Edge Function • Reminder email: 1h before scheduled_at WHERE status='scheduled' AND notifications enabled • Reminder content: title, scheduled time, View + Reschedule deep links • Weekly digest: Monday 8am local time — posts published, impressions, reactions, top post, 3 suggested topics • Unsubscribe link sets notification_preferences toggle to false • Only sent to verified email addresses | US-011,US-020,US-026 | P4 | To Do
US-053 | S6 | Epic 7: Platform | 7.2 Templates | As a user I want to choose from pre-built content templates so that I don't start every post from a blank slate | • /templates route in sidebar • Template categories: Lessons Learned, Project Launch, Hot Take, Tutorial, Career Milestone, Industry Observation, Tool Review, Story • Each card: icon, title, description, 50-word example, 'Use template' button • 'Use template' → content generator with template pre-filled in instructions • 8 built-in templates (one per category, developer persona) • 'Save as template' in content generator saves custom template • My Templates section on /templates page • Delete custom template with confirmation | None | P4 | To Do
US-054 | S6 | Epic 7: Platform | 7.3 Mobile | As a user I want to use core app features on my phone so that I can review drafts and check analytics on the go | • Sidebar collapses to bottom nav on <768px • Bottom nav: Home, Create, Calendar, Engage, Profile (icons + labels) • Content generator: all inputs usable on mobile, no iOS zoom on focus • Draft review: content readable and editable at 375px • Calendar: touch targets ≥44px • Dashboard KPI cards stack vertically • No horizontal scroll at 375px on any core page • Analytics charts use recharts ResponsiveContainer • Extension features labelled 'Desktop Chrome only' on mobile | None | P4 | To Do

## Sprint Plan
LinkedBloom Scribe — Sprint Plan
Sprint | Timeline | Epic Focus | Sprint Goal | Stories | Story Count
S1 | Weeks 1–2 | Epic 1: Platform Foundation Fixes | Fix all broken/incomplete existing functionality. No new features until foundation is solid. | US-001 US-002 US-003 US-004 US-005 US-006 US-007 US-008 US-009 US-010 US-011 US-012 | 12
S2 | Weeks 3–4 | Epic 2: LinkedIn Integration | OAuth, post publishing, analytics pipeline. The beta unlock sprint. | US-013 US-014 US-015 US-016 US-017 US-018 US-019 US-020 US-021 US-022 US-023 US-024 US-025 | 13
S3 | Weeks 5–6 | Epic 3: Analytics Dashboard | Real metrics replace all mock data. Trends page and post import. | US-026 US-027 US-028 US-029 US-030 | 5
S4 | Weeks 7–8 | Epic 4: Engagement Intelligence | Comment drafting tool, inspiration library, feed insights. | US-031 US-032 US-033 US-034 US-035 US-036 US-037 | 7
S5 | Weeks 9–10 | Epic 5: Chrome Extension | Full extension: scaffold, feed detection, comment overlay, quick capture, transparency. | US-038 US-039 US-040 US-041 US-042 US-043 US-044 US-045 US-046 US-047 US-048 | 11
S6 | Weeks 11–12 | Epics 6 & 7: Persona Maturity + Platform | Persona refresh, behavioral signals, emails, templates, mobile polish. | US-049 US-050 US-051 US-052 US-053 US-054 | 6

## Dependency Map
LinkedBloom Scribe — Dependency Map
Story ID | Sprint | Story (short) | Depends On | Blocked By
US-001 | S1 | As a developer I want to run a DB migration adding all missing columns to the po… | None | —
US-002 | S1 | As a user I want my post's topic, tone, instructions, hashtags, and length saved… | US-001 | US-001
US-003 | S1 | As a user I want every version of my post saved automatically so that I can go b… | US-001,US-002 | US-001,US-002
US-004 | S1 | As a user I want to see my actual scheduled and published posts on the calendar … | US-001 | US-001
US-005 | S1 | As a user I want to pick a date/time to schedule my post so that it appears on t… | US-001,US-004 | US-001,US-004
US-006 | S1 | As a user I want to change the scheduled date of a post from the calendar so tha… | US-004,US-005 | US-004,US-005
US-007 | S1 | As a user I want to remove a post from my schedule directly from the calendar so… | US-004,US-005 | US-004,US-005
US-008 | S1 | As a user I want to click Settings in the sidebar and land on a real page so tha… | None | —
US-009 | S1 | As a user I want to update my profile details in Settings so that my persona and… | US-008 | US-008
US-010 | S1 | As a user I want to manage my Gemini and OpenAI API keys in Settings so that con… | US-008 | US-008
US-011 | S1 | As a user I want to configure which notifications I receive so that I'm reminded… | US-008 | US-008
US-012 | S1 | As a user I want to permanently delete all my data from Settings so that I can t… | US-008 | US-008
US-013 | S2 | As a developer I want a linkedin_accounts DB table so that user OAuth tokens can… | None | —
US-014 | S2 | As a user I want to connect my LinkedIn account via OAuth so that the platform c… | US-013 | US-013
US-015 | S2 | As a user I want to see my LinkedIn connection status across the app so that I a… | US-014 | US-014
US-016 | S2 | As a user I want to disconnect my LinkedIn account so that I can revoke access a… | US-015 | US-015
US-017 | S2 | As a developer I want automatic token refresh so that users never have to manual… | US-014 | US-014
US-018 | S2 | As a developer I want a linkedin-publish-post Edge Function so that the client n… | US-014,US-013 | US-014,US-013
US-019 | S2 | As a user I want to publish my post to LinkedIn with one click from the review p… | US-018,US-015 | US-018,US-015
US-020 | S2 | As a user I want scheduled posts to publish automatically at the scheduled time … | US-018,US-017 | US-018,US-017
US-021 | S2 | As a user I want to see a direct link to my published post on LinkedIn so that I… | US-019 | US-019
US-022 | S2 | As a developer I want a post_analytics DB table so that LinkedIn metrics can be … | US-001 | US-001
US-023 | S2 | As a developer I want a linkedin-fetch-analytics Edge Function so that post metr… | US-022,US-014 | US-022,US-014
US-024 | S2 | As a user I want my post analytics automatically refreshed at 24h, 48h, 7d, 14d,… | US-023,US-019 | US-023,US-019
US-025 | S2 | As a user I want a manual 'Refresh metrics' button on published posts so that I … | US-023 | US-023
US-026 | S3 | As a user I want real LinkedIn performance KPIs on my dashboard so that I can un… | US-022,US-023 | US-022,US-023
US-027 | S3 | As a user I want to see my best performing post highlighted on the dashboard so … | US-026 | US-026
US-028 | S3 | As a user I want detailed analytics for each published post so that I can learn … | US-022,US-023,US-026 | US-022,US-023,US-026
US-029 | S3 | As a user I want charts showing my engagement trends over time so that I can ide… | US-026,US-028 | US-026,US-028
US-030 | S3 | As a user I want to import my existing LinkedIn posts so that I have a performan… | US-014,US-023 | US-014,US-023
US-031 | S4 | As a developer I want an engagements DB table so that comment drafting sessions … | US-001 | US-001
US-032 | S4 | As a developer I want a generate-comment-options Edge Function so that both web … | US-031 | US-031
US-033 | S4 | As a user I want to paste a LinkedIn post and get three on-brand comment options… | US-032 | US-032
US-034 | S4 | As a developer I want an inspirations DB table and storage bucket so that users … | None | —
US-035 | S4 | As a user I want to save LinkedIn posts that inspire me to a searchable library … | US-034 | US-034
US-036 | S4 | As a user I want the content generator to consider my saved inspirations so that… | US-034,US-035 | US-034,US-035
US-037 | S4 | As a user I want AI-generated insights about patterns in my saved inspirations s… | US-035 | US-035
US-038 | S5 | As a developer I want a properly structured Manifest V3 Chrome extension project… | None | —
US-039 | S5 | As a user I want to be automatically logged into the extension when I'm logged i… | US-038 | US-038
US-040 | S5 | As a user I want to open the extension popup and see my current status and quick… | US-039 | US-039
US-041 | S5 | As a user I want to see a clear explanation of what the extension monitors on fi… | US-039 | US-039
US-042 | S5 | As a developer I want a MutationObserver that detects LinkedIn feed posts so tha… | US-038 | US-038
US-043 | S5 | As a developer I want local post scoring so that only genuinely high-value posts… | US-042,US-039 | US-042,US-039
US-044 | S5 | As a user I want a subtle indicator on high-opportunity LinkedIn posts so that I… | US-043 | US-043
US-045 | S5 | As a user I want to click a badge and see AI-generated comment suggestions so th… | US-044,US-032,US-039 | US-044,US-032,US-039
US-046 | S5 | As a user I want 'Use this comment' to insert text into LinkedIn's comment box s… | US-045 | US-045
US-047 | S5 | As a user I want to capture a LinkedIn post as a draft inspiration with right-cl… | US-044,US-039 | US-044,US-039
US-048 | S5 | As a user I want to see exactly what the extension has collected in this session… | US-040,US-042 | US-040,US-042
US-049 | S6 | As a user I want to upload content samples and annotate what I like about them s… | US-034 | US-034
US-050 | S6 | As a user I want to be prompted to refresh my persona every 30 days so that my v… | US-009 | US-009
US-051 | S6 | As a user I want my LinkedIn engagement patterns to feed into my persona model s… | US-042,US-050 | US-042,US-050
US-052 | S6 | As a user I want email reminders for scheduled posts and a weekly performance di… | US-011,US-020,US-026 | US-011,US-020,US-026
US-053 | S6 | As a user I want to choose from pre-built content templates so that I don't star… | None | —
US-054 | S6 | As a user I want to use core app features on my phone so that I can review draft… | None | —

## Legend
Legend & Colour Coding
Sprint | Notes
S1 — Weeks 1–2
S2 — Weeks 3–4
S3 — Weeks 5–6
S4 — Weeks 7–8
S5 — Weeks 9–10
S6 — Weeks 11–12
Priority
P0
P1
P2
P3
P4